| NAME | TERM | INTERPRETATION |
| --- | --- | --- |
| PV (AKA) BCWS | Planned Value (AKA) Budgeted Cost of Work Scheduled | What is the estimated value of the work planned to be done? The 50/50 rule states when beginning a task, charge 50% of the PV to its account, (the other 50% upon completion). |
| EV (AKA) BCWP | Earned Value (AKA) Budgeted Cost of Work Performed | What is the estimated value of the work actually accomplished? |
| AC (AKA) ACWP | Actual Cost Actual Cost of Work Performed | What is the actual cost incurred? |
| BAC | (AKA) Budget at Completion | How much did we BUDGET for the TOTAL JOB? |
| NAME | FORMULA | INTERPRETATION |
| Cost Variance (CV) | EV-AC | NEGATIVE is over budget, POSITIVE is under budget. |
| Schedule Variance (SV) | EV-PV | NEGATIVE is behind schedule, POSITIVE is ahead of schedule. |
| Cost Performance Index (CPI) | EV AC | We are getting $____ out of every $1. Cumulative CPI refers to the sum of all individual EVs divided by the sum of all individual ACs. It is used to forecast project cost at completion. |
| Schedule Performance Index (SPI) | EV PV | We are [only] progressing at ___% of the rate originally planned. A value equal to or greater than one indicates a favorable condition and a value less than one indicates an unfavorable condition. |
| Estimate at Completion (EAC) (AKA) Latest Revised Estimate (LRE) NOTE: There are four ways to calculate EAC. The first formula on the right is most often asked on the exam. | BAC CPI AC + ETC AC+BAC-EV AC+(BAC-EV) CPI | As of now, how much do we expect the total project to cost? $_____. 1. Used if no variances from BAC have occurred or will continue at same rate of spending. 2. Actual plus a new estimate for remaining work. Used when original estimate was fundamentally flawed. (In other words used when past assumptions are incorrect.) 3. Actual to date plus remaining budget. Used when current variances are thought to be atypical of the future. (In other words used when variances are not typical.) 4. Actual to date plus remaining budget modified by performance. Used when current variances are thought to be typical of the future. (when variances are expected to remain the same.) |
| Estimate to Completion (ETC) | EAC – AC | How much more will the project cost? |
| Variance at Completion (VAC) | BAC – EAC | How much over budget will we be at the end of the project? |
| NAME | DESCRIPTION | INTEPRETATION |
| Lines of Communication | N x (N-1) 2 | Number of participants multiplied by the number of participants less one divided by two |
| Float (Slack) | Late Finish (LF) – Early Finish (EF) Late Start (LS) – Early Start (ES) | Total Float is calculated by subtracting ES from LS. Free float is defined as the amount of time an activity can be delayed without delaying the early start of any immediately following activities. |
| Slope | Crash Cost – Normal Cost Crash Time – Normal Time | The cost per day of crashing the project. If costs and times are the same regardless of whether they are crashed or normal, the activity can not be expedited. |
| Benefit Cost Ratio (BCR) | Should be greater than 1 | BCR of less than 1 means the costs are greater than the benefits |
| Internal Rate of Return (IRR) | When are they Equal | The rate (interest rate) at which the project inflows (revenues) and project outflows are equal |
| Activity Duration (AD) | Work Quantity Production Rate | First, the volume or quantity of work to be completed must be measured (scope of the activity must be defined). Next, the productivity rate as it relates to the work quantity must be determined. Dividing work quantity by production rate yields an estimate of activity duration. |
| PERT Standard Deviation | (P-O) 6 | Pessimistic minus optimistic divided by 6 |
| PERT Expected Value (AKA Weighted Average or Expected Time) | P +O + (4x most likely) 6 | Optimistic plus pessimistic plus 4 multiplied by the most likely, then divided by 6 |
| Variance of Task Using PERT | (P-0)2 6 | Pessimistic minus optimistic divided by 6 then squared |
| Sigma = Standard Deviation Ex: Misspelled words - 3 sigma one word per page, 6 sigma one word per thousand pages. | 1 sigma = 68.26 2 sigma = 95.44 3 sigma = 99.73 4 sigma = 99.994 5 sigma = 99.987 6 sigma = 99.9997 | 317,400 defects per million = 31.74% defects (or 3,174 defects out of 10,000 doors) 45,600 defects per million = 4.56% defects (or 456 defects out of 10,000 doors) 2,700 defects per million = .27% defects (or 27 defects out of 10,000 doors) 60 defects per million = .006% defects (or .6 defects out of 10,000 doors) 13.3 defects per million = .0013% defects (or .13 defects out of 10,000 doors) 3.4 defects per million = .00034% defects (or .034 defects out of 10,000 doors) |
| Accuracy of Estimates | 3 levels of accuracy | Order of magnitude estimate (initiating) -25% to +75% from actual, Budget estimate (planning) -10% to +25% from actual, definitive estimate (planning) -5% to +10% from actual |
| Marginal Analysis | Optimal quality level is reached at the point where incremental revenue from product improvement equals the incremental cost to secure it. |
| Opportunity Cost | Requires overall analysis | May incorporate NPV, IRR, Payback Period and/or BCR and require judgment |
| Sunk Cost | Requires overall analysis | Past expenditures for a given activity that are typically irrelevant to future decisions |
| Present Value (PrV) (AKA Expected Monetary Value – EMV) | FV__ (1 + r)N | The value today of future cash flows based on the concept that payment today is worth more than payment tomorrow. There are two ways to calculate Present Value. FV = Future Value R = interest rate N = Number of time periods |
| Net Present Value (NPV) | Present value of total benefits – costs | Value of the total benefits (income or revenue) less the costs |
| Future Value (FV) | FV = PV (1+i)N | Money received in the future is worth less than money received today. |
| Working Capital | WC = A - L | Working capital equals current assets (A) minus liabilities (L). |
| Depreciation | 1. Straight Line 2. Accelerated (2 types) | 1. Same amount each year 2a. Double declining balance and 2b. Sum of the years digits |
| Life Cycle Costing (LCC) | LCC = C + Mpw + Epw + Rpw - Spw | Consider operation and maintenance costs in making project decisions. Life cycle costing is a methodology for calculating the whole cost of a system from inception to disposal: Capital cost (C), Maintenance, (M) Energy cost (E) Replacement cost (R) salvage value (S). The pw subscript indicates the present worth of each factor. |

# Text boxes

2

1

3

4

Mt = amount of payment t years from now

R = interest rate (or discount rate)

T = time period

or

*AKA= Also Known As                                               Source: Public Domain Project Knowledge Information		                            Updated 10/2011

“2”

PROJECT MANAGEMENT COST ANALYSIS WORKSHEET

or

PrV =

Mt  _

(1+r)t

N2-N

2

________________